## Index
t

## Agriculture
| Product Name: Farmer’s Climate aid | TRL Level 1
Sl.No | Key objectives (entry gate) | Our supporting doc., data for review | Exit criteria | Key deliverables ( exit gate) | Our supporting doc., data for review
1 | Back of the envelope environment - new approach | https://www.wired.com/story/how-to-get-better-at-back-of-the-envelope-calculations/ Describe in brief how the new environment will look like and how it adds value and addresses the gaps, raw estimated costs | A program sponsor has been identified | Feasibility study (White paper) | Elaborate one at Level 0 Internal sponsors havepromoted the ideas, external peer review are pending. Later on external program managers from Univ and sponsors has to be contacted | https://www.nasa.gov/directorates/heo/scan/engineering/technology/txt_accordion1.html
2 | Research hypothesis formulated | How Basic research principles is to be supported, hypothesis for getting the basic research papers in place to support applied research in lab | Program end-users/customers have been identified | Initial scientific observations reported in journals, conferences, technical reports | Refer to References, Our R&D based articles, our catalogues Survey done, need to shortlist. See links for Canada, also R&D, challenges, IRAP funding, AI, digital, Manufacturing | https://www.biofuelsdigest.com/bdigest/2018/10/01/expanded-technology-readiness-level-trl-definitions-for-the-bioeconomy/
3 | Basic Scientific principles observed | Do basic scientific principles support the concept? Lowest level of software technology readiness. A new software domain is being investigated by the basic research community. This level extends to the development of basic use, basic properties of software architecture, mathematical formulations, and general algorithms | A mission needs statement has been developed- elborate from TRL level 0 | Literature search report | Refer Mission Need stmt samples and develop one , see literature review samples | https://discover.dtic.mil/results/?q=TPMM
4 | Physial laws and assumptions used in new technologies/ sciences defined | Has the technology development methodology or approach been developed? Basic research activities, research articles, peerreviewed white papers, point papers, early lab model of basic concept may be useful for substantiating the TRL level. | Communication with end users and customers has been initiated | Road Map (Draft) | Draft communiation plan, meeting agendas, expected results, funding, labs etc, engagement manager /plan, budget alloted, other players, SWOT analysis, program management | https://fas.org/
5 | Have some concept in mind that might be realizable | Has a reasonable process concept been proposed? Do basic principles (physical and chemical) support the concept? Have scientific observations been reported? Have mathematical formulations of concepts been developed? Do rough calculations support the concept? Do you have operational view and how new views will improve or impact? | Preliminary operational requirements have been defined | Written report of findings and recommendations (preliminary product plan) | operational requirements sample from Level 0 to be elaborated | https://fas.org/asmp/campaigns/MANPADS/2006/DHS%20ST%20TRL%20Prgm%20Mgmt%20Asmnt%20Chart_1.0_d.pdf
6 | Paper studies support basic principles (literature search) | Basic research to lead to: (a) subsequent applied research and advanced technology developments in Defense‐related technologies, and (b) new and improved military functional capabilities in areas such as communications, detection, tracking, surveillance, propulsion, mobility, guidance and control, navigation, energy conversion, materials and structures, and personnel support. Literatures written , published or referred all form the proofs at this level | Program management vision has been developed | Feasibility review meeting | elaborate on identified program manangement at Level 0, various program units, deleverables, roles, program features, benefits transferred, administration . Document the reviews for planned gates, program milestones, deliverables, research outcomes, any delays, show stoppers, any quality price compromise, end users
7 | Formulation of concepts that might be realizable (draft road map), if-then statements | Lowest level of software readiness. Basic research begins to be translated into applied research and development by providing a detailed mathematical formulation. Examples might include a concept that can be implemented in software or analytic studies of an algorithm’s basic properties. An Interface between technologies has been identified with sufficient detail to allow characterization of the relationship. class stub created, further roadmap for upto further levels like 2, 3 | A feasibility white paper has been developed | Mission Identification statement | Elaborate on the feasibility of developing the research basic that can turn out to be a waste of time and money. Show and prove how the envisaged risks are able to be downplayed, reduced and better prospecting and availability of funds, labs, manufacturing units and various unwanted assumptions becoming true | http://gridlab-d.sourceforge.net/wiki/index.php/Technology_Readiness_Levels
8 | Has a potential client mission space been identified | Survey done, need to shortlist. See links for Canada, also R&D, challenges, IRAP funding, AI, digital, Manufacturing | A threat, vulnerability or gap has been identified | Program Management vision | How mission, feasibility study and program offer the insights of the work to be done, estimated time, cost, benefits generated, potential savings, mass production as an utility and how each package is represented as project, working in parallel, critical path, external dependencies , expected outcomes, transfer of technology, IP etc | https://www.asc-csa.gc.ca/eng/funding-programs/programs/default.asp
9 | Identify interest in technology / science e.g sponsor, funding resource like a Open Challenge at NRC | NRC, Mission Innovation, MaRS, VentureLab, Open challenges posted at various Govt websites, IT and engineering projects bids, Inviations to bid, Expression of Interest all offer leads | Initial risks have been identiifed | Description of Leap ahead capability | How mission, feasibility study and program offer the insights of the work to be done, estimated time, cost, benefits generated, potential savings, mass production as an utility and how each work along with DAIR. Capability demostrator features, new capabilites, jump in way of doing, paradigm shift. How this shift helps humans in doing something better, increase productivity, possibility of mass use on earth | https://www.asc-csa.gc.ca/eng/funding-programs/funding-opportunities/default.asp
10 | Know who will perform research and where it will be done | Top R&D labs across North America, see links | Have well know list of reliable labs, managers, industry/ Univ relation partner papers , programs identified list | Documented in proposed R&D tie-ups, collaborations, ventures with PPP , grants and various relations options to shortlist and go-ahead | A formal templated,versioned release of the identiifed R&D activities with supporting proofs | http://mission-innovation.net/our-members/canada/plans-and-priorities/
11 | Product Name:Farmer’s Climate aid | MRL Level 1 |  |  |  | https://cib-bic.ca/en/about-us/mission-and-mandate/
12 | Key objectives (entry gate) | Our supporting doc., data for review |  | Key deliverables ( exit gate) | Our supporting doc., data for review | http://mission-innovation.net/our-members/canada/plans-and-priorities/
13 | Basic Manufacturing implications identified | See MRL_Users_Guide_V12.5.16 for Q&A and provide answers to these in terms of the project harware, network or new process design related maturity that can progress to a higler level and no risks / risk mitigation plan in place | Base doc depicting the high level arch, processes, quality, estimates, to manufacture the units | Basic Manufacturing implications defined and risk mitigation with new process explained | Our engineering doc that enables the product to be fabricated, and uses economic, easily available raw material, less process, less suprervision and be mass produced | https://www.international.gc.ca/world-monde/funding-financement/index.aspx?lang=eng
14 | Product Name: Precision agriculture/satellite farming aids |  |  |  |  | https://ceri.ca/about/funding-support
15 | Key objectives (entry gate) | Our supporting doc., data for review |  | Key deliverables ( exit gate) | Our supporting doc., data for review | https://www.grandchallenges.ca/who-we-are/
16 | Back of the envelope environment - new approach |  |  | Feasibility study (White paper) |  | https://www.feddevontario.gc.ca/eic/site/723.nsf/eng/home
17 | Research hypothesis formulated |  |  | Initial scientific observations reported in journals, conferences, technical reports |  | https://www.grandchallenges.ca/who-we-are/
18 | Basic Scientific principles observed |  |  | Literature search report |  | https://www.canada.ca/en/services/science/institutes.html
19 | Physial laws and assumptions used in new technologies/ sciences defined |  |  | Road Map (Draft) |  | http://www.science.ca/researchcentres.php
20 | Have some concept in mind that might be realizable |  |  | Written report of findings and recommendations (preliminary product plan) |  | https://libguides.uwf.edu/c.php?g=215199&p=1420828
21 | Paper studies support basic principles (literature search) |  |  | Feasibility review meeting
22 | Formulation of concepts that might be realizable( draft road map), if-then statements
23 | Has a potential client mission space been identified
24 | Identify interest in technology / science e.g sponsor, funding resource like a Open Challenge at NRC
25 | Know who will perform research and where it will be done
26 | Product Name:Farmer’s Climate aid | MRL Level 1
27 | Key objectives (entry gate) | Our supporting doc., data for review |  | Key deliverables ( exit gate)
28 | Basic Manufacturing implications identified
29 | Product Name: Agricultural tube farming aids | Level 1
30 | Key objectives (entry gate) | Our supporting doc., data for review |  | Key deliverables ( exit gate) | Our supporting doc., data for review
31 | Back of the envelope environment - new approach |  |  | Feasibility study (White paper)
32 | Research hypothesis formulated |  |  | Initial scientific observations reported in journals, conferences, technical reports
33 | Basic Scientific principles observed |  |  | Literature search report
34 | Physial laws and assumptions used in new technologies/ sciences defined |  |  | Road Map (Draft)
35 | Have some concept in mind that might be realizable |  |  | Written report of findings and recommendations (preliminary product plan)
36 | Paper studies support basic principles (literature search) |  |  | Feasibility review meeting
37 | Formulation of concepts that might be realizable( draft road map), if-then statements
38 | Has a potential client mission space been identified
39 | Identify interest in technology / science e.g sponsor, funding resource like a Open Challenge at NRC
40 | Know who will perform research and where it will be done
41 | Product Name:Farmer’s Climate aid | MRL Level 1
42 | Key objectives (entry gate) | Our supporting doc., data for review |  | Key deliverables ( exit gate)
43 | Basic Manufacturing implications identified