## Index
t

## Agriculture
| Product Name: Farmer’s Climate aid | Level 5
Sl.No | Key objectives (entry gate) | Our supporting doc., data for review | Exit criteria | Key deliverables ( exit gate) | Our supporting doc., data for review
1 | ORD and CONOPS developed | Refer Capability Development Document Template, earlier called ORD.doc, CONOPS Template | Risk Mgmt Plan is updated | ORD and CONOPS | Finalize the drafts
2 | Security assessment updated | Refer SAP-AA-FedRAMP-High-Security-Test-Case-Procedures-Template | Program Cost Analysis is updated | Security assessment(updated) | Scope the security level based on needs, peer review and signoff | https://www.fedramp.gov/templates/
3 | OMB 300 and Acquisition plan completed- | Office of Managament & Budget-OMB, Refer OPM-08_Appx1.pdf | SEMP,TEMP and PMP are updated | Program Definition Document(PDD) | Finalize the drafts
4 | IPT certified readiness for the transition of the technology | Integrated Product Team (IPT) | A CONOPS is developed | OMB 300 Capital Asset plan | As per template and lab, contrator's assets, liabilites
5 | Program Transition Manager assisted in transition documentation developed | TRL 4 Transition template updated and finalised | Security Assessment is updated | Acquisition plan | ACQUISITION PLANS- SUBPARTs 207.1, 7.105
6 | Technology scan and market survey(ongoing) | TRL 4 Technology scan updated and finalised | OMB 300 and Acqusition plan completed | Entry Criteria Checklist | Entry Criteria Checklist.doc
7 | Analysis of Alternatives developed and updated (TRL 5 & 6) | Recommended outline for the AoA plan.doc | The IPT has certified readiness for the transition of the Technology | Analysis of Alternatives (TRL 5 & 6) | AoA plan.doc | http://acqnotes.com/acqnote/acquisitions/alternative-systems-review
8 | Entry Criteria Checklist completed and delivered to the TM | Entry Criteria Checklist.doc | Program Transition Manager has assisted in transiton documentation development | Initital producibility of component technology completed | Producibility of component technology.pdf, Critical Code Software Producibility for Defense.pdf | http://acqnotes.com/acqnote/acquisitions/analysis-of-alternatives
9 | PDD created, appproved and signed (TRL 5 & 6) | Programme Definition Document.doc | Analysis of Alternatives developed | Initial Manufacturing Plan developed | Manufacturing Plan.pdf and Manufacturing management.pdf | https://www.nap.edu/read/12979/chapter/2#7
10 | Director approved transition | Personal meeting and approval | Entry Criteria Checklist is completed and delivered to TM | Risk Management plan (updated) | Refer TRL 4 template
11 |  |  | PDD created | Program Cost Analysis (updated) | Refer TRL 4 template
12 |  |  | Director has approved transition | TEMP (updated) | Refer TRL 4 template
13 |  |  |  | SEMP (updated) | Refer TRL 4 template
14 |  |  |  | PMP (updated) | program_management_plan_0.doc | http://acqnotes.com/acqnote/careerfields/program-management-overview
15 |  |  |  |  | DAU Program Managers Toolkit.pdf, | https://uwaterloo.ca/ist-project-management-office/methodologies/program-management/program-benefit-delivery/program-management-plan
16
14 | Product Name:Farmer’s Climate aid | MRL Level 5
15 | Key objectives (entry gate) | Our supporting doc., data for review | Exit criteria | Key deliverables ( exit gate) | Our supporting doc., data for review
16 | Manufacturing costs/goals identified. Potential material sources identified | Estimates using TCASE tool , using analog estimation-(Technology Cost and Schedule Estimating) | Identification of enabling/critical technologies and components is complete | Manufacturing cost report |  | http://www.dodmrl.com/
17 | Capability to produce prototype components in product relevant environment | Maturity level assessment | Prototype materials, tooling and test equipment, as well as personnel skills have been demonstrated on components in a production relevant environment | Review of MRL_Matrix_V2018 for task completion
| A manufacturing strategy has been refined and integrated with the risk management plan | Manufacturing Strategy.pdf by John Miltenburg |  | Use general strategy template and add diagrams as per Miltenburg's suggestion