## Index
t

## Agriculture
| Product Name: Farmer’s Climate aid | Level 6
Sl.No | Key objectives (entry gate) | Our supporting doc., data for review | Exit criteria | Key deliverables ( exit gate) | Our supporting doc., data for review
1 | Execute TTA/TCA | See TTA template | PDD has been approved and signed | Analysis of Alternatives (TRL 5 & 6)
2 | Program Manager Identified | Internal task | A Program Manager has been identified | Technology Transition Agreement(TTA) or Technology commerisialization agreement(TCA)
3 | Successful Test & evaluation(T&E) in a simulated operational environment conducted | DODD 5000.01 /.02 standards, see Notes, pdfs for testing and eval templates | Risk Management plan, Program Cost Analysis and PMP has been updated | Initial Security Guidelines
4 | End User / customers briefed on the results of T&E | Reports with analysis charts are offered to keep user informed about the progress | SEMP and TEMP updated | Draft Program Assessment rating tool( PART) |  | https://en.wikipedia.org/wiki/Program_Assessment_Rating_Tool
5 | Initial Security Guildelines developed |  | Successful testing and evaluation in a simulated operational environment has been conducted | Risk Management plan (updated)
6 | Draft Program Assessment Rating Tool (PART) plan exists. | See PART template and questionaire | End User / customers has been briefed on the results of the testing | Program Cost Analysis (updated)
7 | NEPA plan | Env assessment plan- NEPA.pdf, MEPA project-management-plan.pdf | Initial Screening Guidelines have been developed | TEMP (updated)
8 | Interoperability assessment | The LISI Interoperability Maturity Model Provides a Common DoD Basis for Requirements Definition and for Incremental System Improvements Net-Ready Key Performance Parameter (NR-KPP) Compliance Checklist From Defense Acquisition Guidebook (DAG) | Analysis of Alternatives updated | SEMP (updated)
9 |  |  | Draft PART plan exists | PMP (updated)
10 |  |  | NEPA plan exists | National Environment Policy Act (NEPA) initial assessment | See NEPA policy
11 |  |  | Interoperability assessment | Interoperability assessment as per The policies for interoperability are found in CJCSI 3170.01 series, JCIDS Manual, and CJCSI 6212.01 series. |  | https://acqnotes.com/acqnote/acquisitions/interoperability
12 | [5 empty] | https://acqnotes.com/acqnote/acquisitions/net-ready-key-performance-parameter-nr-kpp
13
14 | [5 empty] | http://acqnotes.com/acqnote/careerfields/program-management-overview
15 | [5 empty] | https://uwaterloo.ca/ist-project-management-office/methodologies/program-management/program-benefit-delivery/program-management-plan
16
14 | Product Name:Farmer’s Climate aid | MRL Level 6
15 | Key objectives (entry gate) | Our supporting doc., data for review | Exit criteria | Key deliverables ( exit gate) | Our supporting doc., data for review
16 | Capability to produce system prototype in a product relevant environment | Maturity level assessment as per DoD prototyping GuideBook.pdf | Successful testing of the capabilites | Capability assessed and fit for progression, else redo | design_prototyping_methods_state_of_the_art_in_strategies_techniques_and_guidelines.pdf | http://www.dodmrl.com/
17 | Production cost drivers and goals analyzed and set | Manufacturing Strategy.pdf by John Miltenburg | Clear drivers and goals are identified at Unit and Operational levels | Manufacturing plan with Cost related details | DESIGN TO COST HANDBOOK.pdf | https://www.cambridge.org/core/journals/design-science/article/design-prototyping-methods-state-of-the-art-in-strategies-techniques-and-guidelines/560B306A5E799AEE54D30E0D2C1B7063/core-reader
https://opentextbc.ca/principlesofaccountingv2openstax/chapter/describe-and-identify-cost-drivers/
14 | Product Name:Farmer’s Climate aid | Specific to commercialisation
15 | Key objectives (entry gate) | Our supporting doc., data for review | Exit criteria | Key deliverables ( exit gate) | Our supporting doc., data for review
| Finalize Manufacturing Plan | Refine, add data to Manufaturing plan. pdf of Level 5, refer Defense Manufacturing Management Guide for PMs, Notes | Finalized Manufacturing plan | Updated Manufacturing Plan
| Finalize Engineering documentation | Engineering and Manufacturing Development(EMD) related reports, see Engineering release.pdf | Engineering release criteria met | Engineering documentation release | Engineering release is an action that makes configuration documentation available for its intended use and subject to the contractor's configuration control procedures. | https://www.product-lifecycle-management.com/mil-hdbk-61a-5-7.htm
| Update Marketing Plan | Refer Federal Marketing plan template.pdf |  | Updated Marketing Plan | Use earlier TRL plans and refine with actual managers, plans, small business questionnaire etc | https://business.defense.gov/Small-Business/Marketing-to-DoD/
| Develop and implement a test plan for quality control | APPENDIX E CONSTRUCTION INSPECTION AND TESTING QUALITY PLAN of Design-Build Quality Management Plan (QMP) Outline |  | Test plan for quality control | Prepare test plan as per project components | http://acqnotes.com/acqnote/careerfields/guide-to-marketing-to-the-dod
|  |  |  | Development phase review meeting | Overall review to see complete coverage, scope,